## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Ewheelz Testing
Program Manager | Youtianjian Li
Project Manager | Yuan Li
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | Labels | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2022-07-24 | Youtianjian Li | Can not interact with Journey Date | User tickets | Executing/Controlling | Testing | Medium | Youtianjian Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear | New
2 | 2022-07-24 | Youtianjian Li | Click on "Ckeck availability" Button | User tickets | Executing/Controlling | Testing | Medium | Youtianjian Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2022-07-24 | Youtianjian Li | No warning message | User tickets | Executing/Controlling | Testing | High | Youtianjian Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear | In Progress | Medium | Initiating | Concept
4 | 2022-07-24 | Youtianjian Li | No warning message | User tickets | Executing/Controlling | Testing | Medium | Youtianjian Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear | Completed | Low | Planning | Requirements
5 | 2022-07-24 | Youtianjian Li | No limited characters | Testimonials | Executing/Controlling | Testing | Medium | Youtianjian Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear |  |  | Executing/Controlling | Design
6 | 2022-07-24 | Youtianjian Li | font size is 12 px | Testimonials | Executing/Controlling | Testing | Low | Youtianjian Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear |  |  | Closing | Development
7 | 2022-07-24 | Yuan Li | No show password option to view the password | admin user management | Executing/Controlling | Testing | Low | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear |  |  |  | Testing
8 | 2022-07-24 | Yuan Li | No error message | admin user management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear |  |  |  | Documentation and Training
9 | 2022-07-24 | Yuan Li | No forget password option | admin user management | Executing/Controlling | Testing | High | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear |  |  |  | Deployment
10 | 2022-07-24 | Yuan Li | Admin panel can not automatically logout in case of inactivity | admin user management | Executing/Controlling | Testing | Low | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear |  |  |  | Post-Deployment
11 | 2022-07-24 | Yuan Li | Admin can not add users from the admin panel. Admin must be provided with user registration form | admin user management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
12 | 2022-07-24 | Yuan Li | All the users can not get added | admin user management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
13 | 2022-07-24 | Yuan Li | All the provided user information can not be accepted and database must get updated | admin user management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
14 | 2022-07-24 | Yuan Li | Users not get added in bulk | admin user management | Executing/Controlling | Testing | Low | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
15 | 2022-07-24 | Yuan Li | Admin can not add route | admin routes management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
16 | 2022-07-24 | Yuan Li | Admin can not delete route | admin routes management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
17 | 2022-07-24 | Yuan Li | Admin can not add details | admin travel management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
18 | 2022-07-24 | Yuan Li | Admin can not delete travel | admin travel management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
19 | 2022-07-24 | Yuan Li | Admin can not view detials travel | admin travel management | Executing/Controlling | Testing | Medium | Yuan Li | 2022-07-24 | 2 | Under Review |  | 2022-07-27 | 3 | Requirements were not clear
Note on F10: Choose from the drop down box.
Note on G10: Choose from the drop down box.
Note on H10: Choose from the drop down list
Note on L10: Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).