## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
1 | Disagreement on the module test project | 2022-07-25 | When the team is testing, modify the test script for the module problem of the application | High | Vijay Shrestha | Test manager | 301 | Analyze and discuss test requirements and determine test objectives
2 | Extension of expected module completion time | 2022-07-28 | Due to poor prediction of module difficulty, some module use cases were delayed | High | Yuan Li | Manager | 302 | Need to complete the test of the module as soon as possible
3 | Divergence appears in the part of the template that needs to be filled in | 2022-07-29 | Not clear about what needs to be filled in | Medium | Youtianjian Li | Scribe | 303 | Disagreements need to be resolved peacefully

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
1 | 301 | Test each function of the module separately | 2022-07-25 | High | Vijay Shrestha | Done | This issue has been solved
2 | 302 | Teamwork to help complete use cases for some complex modules | 2022-07-28 | High | Yuan Li | Done | This issue has been solved
3 | 303 | Group brainstorming to solve the content to be filled | 2022-07-29 | Medium | The Oracle | Done | This issue has been solved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
1 | 2022-07-25 | Determine what needs to be tested in the module | High | 1 | Group decision
2 | 2022-07-28 | The group discusses the progress of the test and what needs to be revised | High | 2 | Group decision
3 | 2022-07-29 | Determine the final content to be filled in the relevant documents | Medium | 3 | Group decision

## Team
INFO6068 | Capstone Project
Team Name: | The Oracle
Members: | Vijay Shrestha
Youtianjian Li
Dhaval Prahladkumar Patel
Yuan Li