## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
1 | Diffculty in determing in scope and out of scope for testing. | 2022-06-01 | The team faced difficulty in determining the in scope and out of scope content for testing. | Delay in creation of test plan document | Krystine Yuan Li | Scribe | 201 | This issue was addressed as soon as possible
2 | Difficulty in adjusting deadline changes. | 2022-06-07 | Some changes in the project caused some tight deadlines. The team faced difficult in adjusting the deadline so that project flows smoothly. | Delayed the development of project plan | Dhaval Prahladkumar Patel | Resournce Manager | 202 | This issue wad addressed by carefully evaluating the project progress and continous conversation with the stakeholders.
3 | Difficulty in determining the testing approach. | 2022-06-05 | The team faced challenges in determining which test to automate and which not. | Slightly delayed the test plan development process | Vijay Shrestha | Project Manager | 203 | The issue was addressed by careful discussion among the team members
4 | Difficulty in determinign the test environment. | 2022-06-06 | Difficulty in identifying the best testing environment for the project. | Poor testing environment can cuase testing mishaps and ulimately result in poor quality product | Youtianjian Li | Steering Committee | 204 | The issue was addressed by discussion among the team members

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
1 | 201 | Team meeting was conducted to find in-scope and out-scope objectives for the project. | 2022-06-02 | Slightly impacted the initial project progress | Krystine Yuan Li | Solved | This issue has been solved
2 | 202 | Stakeholder meeting was conducted to adjust the deadlines. | 2022-06-08 | Slightly impacted the initial project progress | Dhaval Prahladkumar Patel | Solved | This issue has been solved
3 | 203 | Team meeting was conducted to determine which test to automate and which not. Testing approach was also determined. | 2022-06-07 | Slightly impacted the initial project progress | Vijay Shrestha | Solved | This issue has been solved
4 | 204 | To determine the best testing environment, the product was examined carefully and test cases were studied. | 2022-06-09 | Slightly impacted the initial project progress | Youtianjian Li | Solved | This issue has been solved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
1 | 2022-06-02 | After carefully evaluation, testing scope and out of scope were finalized. Details can be found in the test plan document. | Helped to determine the in scope and out scope for testing. | 201 | This was group decision
2 | 2022-06-08 | Deadlines were adjusted by running some tasks parallely and effective communication with the stakeholders. | Helped to provide the deliverables on time. | 202 | This was group decision
3 | 2022-06-07 | Testing approach was defined by carefully evaluating the test cases and functionality as well as non-functional requirement of the product. | Helped to develop accurate test cases. | 203 | This was group decision
4 | 2022-06-09 | Team meeting was conducted to finalize the testing environment. The testing environment was created based on the test cases. | Helped to test the system effectively. | 204 | This was group decision

## Team
INFO6068 | Capstone Project
Team Name: | The Oracle
Members: | Vijay Shrestha Youtianjian Li Krystine Yuan Li Dhaval Prahladkumar Patel