## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
1 | Synchronize Meeting | 2022-05-19 | One of our team members was outside Canada and we were having some issues with conducting synchronized meetings. | Was not able to submit initial project plan on time | Dhaval Prahladkumar Patel | Resource Manager | 101 | This issue was addressed as soon as possible
2 | Project Plan Development | 2022-05-20 | Not all the team members were used to with MS Project in order to create project plan. | Delayed the development of project plan | Krystine Yuan Li | Scribe | 102 | This issue was addressed by peer-to-peer assistance and watching tutorials
3 | Task Delegation | 2022-05-19 | In order to make test strategy, it was significant to delegate the task as per the team member's expertise. | Slightly delayed the test strategy development process | Vijay Shrestha | Project Manager | 103 | The issue was addressed by careful discussion among the team members
4 | Difficulty in finding testing utilities | 2022-05-20 | Difficulty in identifying the best testing utilities that are popular and best suited for our project. | Inclusion of unpopular testing utilities in the test strategy document | Youtianjian Li | Steering Committee | 104 | The isseue was addressed by discussion among the team members

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
1 | 101 | Favorable timing for all the team members were figured out and virtual meetings were conducted | 2022-05-20 | Slightly impacted the initial project progress | Dhaval Prahladkumar Patel | Solved | This issue has been solved
2 | 102 | Peer-to-Peer assistance sessions were conducted and lots of tutorials were watched to know about project plan development in MS Project software | 2022-05-22 | Slightly impacted the initial project progress | Krystine Yuan Li | Solved | This issue has been solved
3 | 103 | Each team members were interviewed informally to know about their expertise and tasks were delegated accordingly | 2022-05-21 | Slightly impacted the initial project progress | Vijay Shrestha | Solved | This issue has been solved
4 | 104 | This issue was discussed during virtual team meetings and favorable testing utlitlies were discovered for our project | 2022-05-22 | Slightly impacted the initial project progress | Youtianjian Li | Solved | This issue has been solved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
1 | 2022-05-20 | Virtual meeting to be conducted at 7 PM EST. Twice a week | Helped to meet the deadlines on time | 101 | This was group decision
2 | 2022-05-22 | For any unkown technology peer-to-peer assistance session will be conducted | Helped to gain the knowledge of unkown technology and put the project on track | 102 | This was group decision
3 | 2022-05-21 | Task will delegated based on the expertise of team members | Helped to get quality work on time | 103 | This was group decision
4 | 2022-05-22 | Any dilemma about the project will be discussed on the group and in case of multiple point of view, voting will take place | Helped to get quality work on time | 104 | This was group decision

## Team
INFO6068 | Capstone Project
Team Name: | The Oracle
Members: | Vijay Shrestha Youtianjian Li Krystine Yuan Li Dhaval Prahladkumar Patel